## First Audit Remakrs Sheet
S No | CMMI Process Name | Project Name | Issue Description | Responsibilies | Status Naufar | Status FPSC | Remakrs By Ali Raza |  |  | Location FPSC | Location Naufar
1 | REQM | Nafuar | Approval Email for Acceptance of IR in case of Nafuar Project | Abdullah | done | Not requried
2 |  | Nafuar | Typing mistake in PRC flow diagram replace PRC to CAB | Abdullah (Naufar & FPSC) | done | Done in FPSC |  |  | Observation communicated to Abdulllah
3 |  | FPSC / Naufar | In tracability matrix add new column label as "Test Case No" | Umar (Naufar) & Ali (FPSC) | Done In Naufar | Done in FPSC | https://docs.google.com/spreadsheets/d/1lQ0fmgNEIEdgs_RvosoUhJgaRYAjJOas/edit#gid=649396676
4 |  | FPSC / Naufar | Make Avedance Document for approval of QA,SRS/IR, Testcase review and for tracability matrix and must be approved by PM on stepnex template. | Abdullah (Naufar) Ali (FPSC) | Done In Naufar | Done in FPSC | https://drive.google.com/drive/u/0/folders/1CK9YHQKqkmqkTXig1AsGwSywsbqaCNpX |  |  | PMC\FPSC\SS-FPSC-PMC-UAT\SS-FPSC-PMC-Internal Stepnex | PMC\Naufar\SS-Naufar-PMC-Internal Letters Stepnex
5 | PP | FPSC / Naufar | Use your own project life cycle and mention it in project plan remove ejile from project plan | Abdullah for both | I have removed the word agile and sprint from PP and PMC procdure files in both projects |  |  |  | Procedure files updated
6 |  | FPSC / Naufar | Prepare Project Life Cycle docuemnt for Setnex in case of using company's own life cycle.
7 |  | FPSC / Naufar | Make a NON HR resources Sheet and reflect it in Project Plan | Umar(Naufar) Ali(FPSC) | Done | Done in FPSC | Reflected in Project Plan | https://drive.google.com/drive/u/0/folders/10gFRCIAjFGVXLq_lFTSnIDxDINXI3fyg | Observations communicated to Ali
8 |  | FPSC / Naufar | Make a table add two columns one for Avalible skill set and second for Required skill set and reflect it in Project plan | Umar(Naufar) Ali(FPSC) | Done | Done in FPSC | Reflected in Project Plan | https://drive.google.com/drive/u/0/folders/10gFRCIAjFGVXLq_lFTSnIDxDINXI3fyg
9 |  | FPSC / Naufar | Add internal stakholders in team angagement plan and reflect it in PIID and external in Contract | Not Required
10 |  | FPSC / Naufar | Make Stackholder idendification matrix and reflect it in project plan and matrix columns will be Name, Role assigned, Email | Umar(Naufar) Ali(FPSC) | Done | Done in FPSC | Reflected in Project Plan | https://drive.google.com/drive/u/0/folders/10gFRCIAjFGVXLq_lFTSnIDxDINXI3fyg
11 |  | FPSC / Naufar | All plans like QA plan, testing plan and all others should map in Project Plan. | All plans like QA plan, testing plan and all others should map in Project Plan. |  |  | Pending
12 |  | FPSC / Naufar | Make Hr Replacement sheet and reflect it in Project plan | Abdullah (Naufar) Ali (FPSC) | Not requried in Nuafar case |  | HR replacement sheet is not updated in project plan because i did not get information from wajid yet | https://drive.google.com/drive/u/0/folders/10gFRCIAjFGVXLq_lFTSnIDxDINXI3fyg
13 | PMC | FPSC / Naufar | Make an avidance document for regular review meeting with the team for monitering and fix frequancy for last 3 months. | Abdullah (Naufar) Ali (FPSC) | Done | Done in FPSC | https://drive.google.com/drive/u/0/folders/1kRAkUA7Vq0Gi09jiqXcDoyw2MHERx2Qw |  | observations communicated with both |  | PMC\Naufar\SS-Naufr-PMC-MOMs
14 |  | FPSC / Naufar | Make a document for milestone review meeting for both cases either it may be completed or failuar | Abdullah (Naufar) Ali (FPSC) | Done | Done in FPSC | https://drive.google.com/drive/u/0/folders/1t95MNfZ86yj4e3ebISJn-7HMKVTwS5_P |  |  | PMC\FPSC\SS-FPSC-PMC-UAT\SS-FPSC-PMC-Interal MOMs | PMC\Naufar\SS-Naufr-PMC-MOMs
15 |  | FPSC / Naufar | Delay in any task or in milestone add it like an issue in issue log. | Umar(Naufar) Ali(FPSC) | Done | Already Done in FPSC | Already Done in FPSC
16 |  | FPSC / Naufar | Add root cause in issue log just before action column | Umar(Naufar) Ali(FPSC) | Done | Done in FPSC | https://docs.google.com/spreadsheets/d/1_Vi2mMsPUI68BGa7p4Em2vvvg4qv0-M5/edit#gid=9000749