## Detail Estimation Sheet
Estimation Sheet Module Wise |  |  |  | FALSE
S No. | Req#(SRS) | Feature List | Assignee | Assigned To | Estimated Duration (Hours) | Start Date | End Date
1 | TIMENEX-IR-EMP-01 | Login to System | PM | Dev 2 | 4 | 2019-03-11 | 2019-03-11
2 | TIMENEX-IR-EMP-02 | creation of employee | PM | Dev 2 | 4 | 2019-03-11 | 2019-03-11
3 | TIMENEX-IR-EMP-03 | Deactivation and Activation of employee | PM | Dev 2 | 2 | 2019-03-12 | 2019-03-12
4 | TIMENEX-IR-EMP-04 | Edit/Update Employee | PM | Dev 2 | 2 | 2019-03-12 | 2019-03-12
5 | TIMENEX-IR-EMP-05 | View employee list | PM | Dev 2 | 4 | 2019-03-12 | 2019-03-12
6 | TIMENEX-IR-EMP-06 | Delete employee | PM | Dev 2 | 4 | 2019-03-13 | 2019-03-13
7 | TIMENEX-IR-EMP-07 | Search employee(User can serch emplyee using employee number etc.) | PM | Dev 2 | 4 | 2019-03-13 | 2019-03-13
8 | TIMENEX-IR-SHF-01 | Navigate to Shifts | PM | Dev 2 | 4 | 2019-03-14 | 2019-03-14
9 | TIMENEX-IR-SHF-02 | creation of Shift | PM | Dev 2 | 4 | 2019-03-14 | 2019-03-14
10 | TIMENEX-IR-SHF-03 | Add start and end hours | PM | Dev 2 | 6 | 2019-03-15 | 2019-03-15
11 | TIMENEX-IR-SHF-04 | Shift Applicable days | PM | Dev 2 | 5 | 2019-03-15 | 2019-03-18
12 | TIMENEX-IR-SHF-05 | Assign unit to shift | PM | Dev 2 | 6 | 2019-03-18 | 2019-03-19
13 | TIMENEX-IR-SHF-06 | Deactivation and Activation of Shift | PM | Dev 2 | 4 | 2019-03-19 | 2019-03-19
14 | TIMENEX-IR-SHF-07 | Edit/Update Shift | PM | Dev 2 | 4 | 2019-03-20 | 2019-03-20
15 | TIMENEX-IR-SHF-08 | View Shift list | PM | Dev 2 | 4 | 2019-03-21 | 2019-03-21
16 | TIMENEX-IR-SHF-09 | Delete Shift | PM | Dev 2 | 2 | 2019-03-21 | 2019-03-25
17 | TIMENEX-IR-SHF-10 | Search Shift(User can serch shift using name or id etc.) | PM | Dev 4 | 5 | 2018-01-08 | 2018-03-08 | 2018-05-08
18 | TIMENEX-IR-ROL-01 | Login to System | PM | Dev 4 |  | 2018-01-08 | 2018-03-08 | 2018-05-08
19 | TIMENEX-IR-ROL-02 | Creation multiple roles with description | PM | Dev 4 |  | 2018-01-08 | 2018-05-08 | 2018-08-08
20 | TIMENEX-IR-ROL-03 | Update and delete functnality | PM | Dev 2 | 4 | 2019-03-25 | 2019-03-25
21 | TIMENEX-IR-ROL-04 | Role List | PM | Dev 2 | 4 | 2019-03-25 | 2019-03-26
22 | TIMENEX-IR-ROL-05 | Search Role | PM | Dev 2 | 4 | 2019-03-26 | 2019-03-26
23 | TIMENEX-IR-USE-01 | Navigate to Users | PM | Dev 4 |  | 06/08-2018 | 2018-08-08 | 2018-10-08
24 | TIMENEX-IR-USE-02 | Creation of user | PM | Dev 2 | 6 | 2019-03-27 | 2019-03-27
25 | TIMENEX-IR-USE-03 | Assign role to user | PM | Dev 1 | 4 | 2019-03-27 | 2019-03-28
26 | TIMENEX-IR-USE-04 | Assign unit to user | PM | Dev 4 |  | 2018-09-08 | 2018-10-08 | 2018-12-08
27 | TIMENEX-IR-USE-05 | Update and delete functnality | PM | Dev 2 | 3 | 2019-03-28 | 2019-03-28
28 | TIMENEX-IR-USE-06 | User List | PM | Dev 2 | 2 | 2019-03-28 | 2019-03-28
29 | TIMENEX-IR-USE-07 | Search User | PM | Dev 2 | 1 | 2019-03-28 | 2019-03-28
30 | TIMENEX-IR-PER-01 | Navigate to Permissions | PM | Dev 2 | 1 | 2019-03-28 | 2019-03-28
31 | TIMENEX-IR-PER-02 | Create Module or permissions | PM | Dev 2 | 8 | 2019-03-29 | 2019-03-29
32 | TIMENEX-IR-PER-03 | Individual role has its own permissons | PM | Dev 4 | 18 | 2018-11-08 | 20/08/2018 | 23/08/2018
33 | TIMENEX-IR-PER-04 | User can visit only those module which permission is granted to him | PM | Dev 1 | 12 | 2019-03-28 | 2019-03-29
34 | TIMENEX-IR-PER-05 | Update and delete functnality | PM | Dev 1 | 4 | 2019-03-27 | 2019-03-27
35 | TIMENEX-IR-PER-06 | Permission/Module lists | PM | Dev 1 | 3 | 2019-03-27 | 2019-03-27
36 | TIMENEX-IR-PER-07 | Search Permssions | PM | Dev 4 | 1 | 21/08/2018 | 23/08/2018 | 25/08/2018
37 | TIMENEX-IR-ROS-01 | Roster Creation | PM | Dev 1 | 80 | 2019-03-13 | 2019-03-26
38 | TIMENEX-IR-ROS-02 | Select Unit for Roster | PM | Dev 1 | 1 | 2019-03-27 | 2019-03-27
39 | TIMENEX-IR-ROS-03 | Select Number of days | PM | Dev 1 | 1 | 2019-03-12 | 2019-03-12
40 | TIMENEX-IR-ROS-04 | Select Start date | PM | Dev 1 | 1 | 2019-03-12 | 2019-03-12
41 | TIMENEX-IR-ROS-05 | Select Shifts which you want to include in this roster | PM | Dev 3 | 12 | 2019-03-11 | 2019-03-12
42 | TIMENEX-IR-ROS-06 | Shift requirment UI in roster | PM | Dev 1 | 6 | 2019-03-12 | 2019-03-12
43 | TIMENEX-IR-ROS-07 | Add Remove Employee in roster | PM | Dev 3 | 12 | 2019-03-12 | 2019-03-13
44 | TIMENEX-IR-ROS-08 | Roster List | PM | Dev 3 | 2 | 2019-03-14 | 2019-03-14
45 | TIMENEX-IR-ROS-09 | Emloyee Shift assignment in roster | PM | Dev 1 | 8 | 2019-03-11 | 2019-03-11
46 | TIMENEX-IR-ROS-10 | Genrate for full year | PM | Dev 3 | 62 | 2019-03-14 | 2019-03-25
47 | TIMENEX-IR-REP-01 | Unit Wise report | PM | Dev 3 | 16 | 2019-03-26 | 2019-03-27
48 | TIMENEX-IR-REP-02 | Employee Wise report | PM | Dev 3 | 16 | 2019-03-28 | 2019-03-29
360