## GANTT CHART
Project Management Plan/ Gantt Chart For Project Biometric Attandance Management and Monitoring System For KP Naufar
|  | January |  | Febuary |  |  |  | March | Apr
| G A N T T C H A R T ---------------------- G A N T T C H A R T ----------------------- G A N T T C H A R T | Phases | Task Name |  | Duration | Start | Finish | Mile Stone
|  |  | Project Management for GRM |  | 91 Days | Sun 13/01/19 | Mon 15/04/19
|  | INITIATING | 1. Initiating |  | 8 days | Sun 13/01/19 | Sun 20/01/19
|  |  | 1.1 Prepare Inception Report |  | 6 days | Sun 13/01/19 | Fri 18/01/19
|  |  | Identify Goals and Objectives |  | 1
|  |  | Develop Strategies and Plans |  | 1
|  |  | Research Previous Experience |  | 1
|  |  | Draft Inception Report |  | 3
|  |  | 1.2 Develop Hardware Procurment Plan |  | 2 days | Sat 19/01/19 | Sun 20/01/19
|  |  | Determine Procurement Requirements |  | 0.5
|  |  | Document Request For Proposals(RFP) for HW Equip |  | 0.5
|  |  | Identify Potential HW Equipment Providers |  | 0.5
|  |  | Issue Requisition Documents |  | 0.5
|  |  | Submission of Inception Report |  |  |  |  | Sun 20/01/19
|  | PLANNING & Development | 2. Planning & Development |  | 25 days | Jan 21/01/19 | Sun 10/03/19
|  |  | 2.1 System Study,Gap Analysis & SRS |  | 8 days | Jan 21/01/19 | Sat 02/02/19
|  |  | Meeting with Stakholders and Existing System Study |  | 2
|  |  | Identification of Gaps & Data Collection |  | 2
|  |  | Analysis Report & Finalization of Requirments with Stakholders |  | 2
|  |  | Softwarre Requirments Specification (SRS) |  | 2 day | Wed 30/01/19 | Sat 02/02/19 | Thu 31/01/19
|  |  | 2.2 Development of Prototypes |  | 17 days | Sun 03/02/19 | Thu 06/12/18
|  |  | Maping System Process Flows |  | 5
|  |  | System High Level Design |  | 3
|  |  | System User Interface and wire Frames |  | 5
|  |  | Functional Prototypes |  | 4 | Mon 2/12/18 | Thu 06/12/18 | Thu 14/02/19
|  | EXECUTING | 3. Implementation & Executing
3.1 Hardware Installation and Configuration
|  |  | Hardware Installed and Configured |  |  |  |  | Wed 20/03/19
3.2 System Implementaaion
2.3 System Customization and Development
Low Level Design
Customization and Prototype Realization
System Integration and Testing
System Developed and Ready for Implemenation
|  |  | System Implemented |  |  |  |  | Sat 23/03/19
|  |  | Registration and Trainings |  |  |  |  | Mon 25/03/19
|  |  | User Acceptance Test |  |  |  |  | Wed 27/03/19
3.4 Go Live
Test Live
|  |  | Go Live |  |  |  |  | Mon 01/04/19
4. Maintenance Support
|  | MONITORING & CONTROLLING | 5. Monitoring and Controlling
5.1 Monitor and Control Project Work
Authorize Project Work
Manage Action Items
Manage Project Progress
5.2 Integrated Change Control
Manage Scope
Manage Requirements
Control Changes
5.3 Schedule Control
Track Status
Maintain Project Schedule
Maintain Work Plans
5.4 Produce Performance Reports
Report Weekly Status
Report Monthly Status
5.5 Manage Stakeholders
Monitor Satisfaction
Resolve Issues
5.6 Risk Monitoring and Control
Manage Risks
|  | CLOSING | 6. Closing
6.1 Close Project
Assess Satisfaction
Summarize Project Results and Lessons Learned
Review and Recognize Team Performance
|  |  | Final Report |  |  |  |  | Mon 15/04/19
Close Out the Project Records
|  |  | 6.2 Contract Closure |  | 1 day
|  |  | Close Contract |  | 1 day
Note: After Contract Closure SLA would be signed
KEY:
Milestone / delvierable for StepNex
Project phase
Sub-phases
Kick off
Jan 13, 2019
# 2
Jan 31
SRS
Milestones
# 1
Jan 20
Inception Report
# 3
Feb 14
Prototypes
# 4
Mar 20
HW Installation
# 5
Mar 23
Sys Imp
# 6
Mar 25
Registration &Trainings
# 9
Apr15
First Report
# 7
Mar 27
UAT
Jan 20
Jan 13
Jan 21
Mar 09
Mar 10
Mar 31
Jan 21
Apr 15
Apr 15
Apr 7
Apr 15
Phase-I: Initiating
Phase-II: Planning & Dev
Phase-III: Executing & Imp
Phase-IV: Operationalization Support
Phase-V: Monitoring and Control
Phase-VI: Closing
Closure
Apr 15, 2019
# 8
Apr 1
Go Live
Apr 1